## HIRDLS_checklist
Data Preservation Content Spec Reference |  | Item |  | Format | HIRDLS Internal Document Number | Size | Delivery Status | Target Archive Location | Type of Service | Notes
SECTION 3.1 | Preflight/Pre-Operations Calibration
3.1.1 | Instrument Description
|  | HIRDLS Acronyms, Abbreviations, Dictionary of Terms and Optical System Terminology |  | pdf | TC-HIR-149 | 161KB | Submitted May 21, 2013
INSTRUMENT LEVEL REQUIREMENTS/SPECIFICATIONS
|  | Interface Control Documents |  | folder-pdf files | ICDs | 7.69MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Subsystem Specifications |  | folder-pdf files | Subsysytem Specs | 2.91MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Radiometric Calibration Error Budget (RADCALAC) |  | folder | TC-OXF-118 | 70.1KB | Submitted May 21, 2013
|  | Science Requirements Document (SRD) |  | pdf file | SC-HIR-012C | 295KB | Submitted May 21, 2013
|  | Instrument Requirements Document (IRD) |  | pdf file | SC-HIR-018L | 166KB | Submitted May 21, 2013
|  | Instrument Technical Specification (ITS) |  | pdf file | SP-HIR-013U | 348KB | Submitted May 21, 2013
|  | Detailed Optical Design Specifications |  | pdf file | SP-HIR-053 | 386KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Spectral Requirements |  | pdf file | SP-HIR-069C | 82.3KB | Submitted May 21, 2013
|  | Out-of-Band Spectral Blocking Requirements |  | pdf file | SP-HIR-154A | 40.9KB | Submitted May 21, 2013
|  | Spectral Performance and Spectral Verification Requirements for HIRDLS Optical Elements |  | pdf file | SP-HIR-155 | 180KB | Submitted May 21, 2013
|  | Baseline Scan Patterns for HIRDLS Design and Test |  | pdf file | SP-HIR-198 | 39.6KB | Submitted May 21, 2013
|  | Science Algorithm Implementation Language (SAIL) Requirements Document |  | pdf file | SW-HIR-147C | 458KB | Submitted May 21, 2013
|  | Science Algorithm Implementation Language (SAIL) High-Level Specification Document |  | pdf file | SW-LOC-0117A | 253KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Optical System Specification Document |  | pdf file | TC-HIR-032 | 0.97MB | Submitted May 21, 2013
|  | System Performance Requriements and Allocation Tables (SPRAT) |  | pdf file | TC-HIR-057H | 267KB | Submitted May 21, 2013
|  | Radiometric and Line of Sight Verification Requirements |  | pdf file | TC-HIR-124 | 593KB | Submitted May 21, 2013
|  | HIRDLS Alignment Definitions |  | pdf file | TC-HIR-197A | 91KB | Submitted May 21, 2013
|  | Allocation of the ITS Radiometric Gain Stability Requirement |  | pdf file | TC-LOC-236D | 127KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Line-Of-Sight (LOS) Flow Down Charts |  | cvs | TC-LOC-296.zip | 258KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Signal Processing of Radiometric Data in the HIRDLS Instrument |  | pdf file | TC-NCA-018 | 25.7KB | Submitted May 21, 2013
|  | SRD to IRD Flowdown Matrix |  | pdf file | TC-NCA-033 | 139KB | Submitted May 21, 2013
|  | Scan Mirror Angles and LOS Direction |  | pdf file | TC-OXF-028b | 163KB | Submitted May 21, 2013
|  | On the derivation and interpretation of the IRD pointing requirements |  | pdf file | TC-OXF-068 | 23.9KB | Submitted May 21, 2013
|  | A note on the choice of HIRDLS chopper frequency |  | pdf file | TC-OXF-69 | 463KB | Submitted May 21, 2013
|  | Signal-to-noise ratios for atmospheric views |  | pdf file | TC-OXF-089A | 23.4KB | Submitted May 21, 2013
|  | HIRDLS RADMETAC Budget Description document |  | pdf file | TC-OXF-097A | 2.62MB | Submitted May 21, 2013
|  | Jitter Definitions and Requirements |  | pdf file | TC-OXF-098A | 48KB | Submitted May 21, 2013
|  | HIRDLS- Stray light and Thermal Background Control Requirements and Preliminary Estimates of Background Signals at the Detectors |  | pdf file | TC-RAL-043C | 706KB | Submitted May 21, 2013
INSTRUMENT LEVEL AS-BUILT CONFIGURATIONS
Subsystem End Item Data Packages
|  |  | Cooler Subsystem (CSS) | various | EIDP_CSS | 110MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | Detector Subsystem (DSS) | various | EIDP_DSS | 124MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | Gyro Subsystem (GSS) | various | EIDP_GSS | 7.59MB | Submitted May 21, 2013
|  |  | In-Flight Calibrator Subsystem (IFC) | various | EIDP_IFC | 14.7MB | Submitted May 21, 2013
|  |  | Instrument Processor Subsystem (IPS) | various | EIDP_IPS | 100MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | Power Subsystem (PSS) | various | EIDP_PSS | 84.2MB | Submitted May 21, 2013
|  |  | Sunshield Subsystem (SSH) | various | EIDP_SSH | 31.7MB | Submitted May 21, 2013
|  |  | Structure Thermal Subsystem (STH) | various | EIDP_STH | 33.9MB | Submitted May 21, 2013
|  |  | Space View Aperture (SVA) | various | EIDP_SVA | 37.9MB | Submitted May 21, 2013
|  |  | Telescope Subsystem (TSS) | various | EIDP_TSS | 169MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Released Drawings (from LOC, original file folder) - Lockheed drawings only, does not contain detailed drawings from HIRDLS subsystems provided by other organizations or vendors |  | 500 pdf files | Lockheed Released Drawings | 193MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Drawing Tree - HIRDLS Instrument |  | pdf file | 1A27750 | 434KB | Submitted May 21, 2013
|  | Mate De-mate Log |  | pdf | LG-LOC-886 | 5.67MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Materials and Processes List |  | pdf | PA-LOC-248a | 1.61MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Limited Life Items Log |  | pdf | PA-LOC-380 | 450KB | Submitted May 21, 2013
|  | HIRDLS Parts List |  | xls | PL-HIR-165P | 1.28MB | Submitted May 21, 2013
|  | As-Built Configuration List, sections 1 & 2 |  | xls | PM-LOC-1081 | 1.25MB | Submitted May 21, 2013
|  | Unverified Failures |  | pdf | PM-LOC-1099 | 82.3MB | Submitted May 21, 2013
|  | Limited Life Items and Test Constraints (Draft only) |  | pdf | SP-HIR-366_Draft | 222KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | System Limited Life Items |  | pdf | TC-LOC-0547 | 12.1KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Waivers / Discrepancies & Corrective Actions Lists |  | pdf | TR-LOC-1093 | 646KB | Submitted May 21, 2013 |  | Lockheed proprietary
INSTRUMENT LEVEL VERIFICATION
Analyses Reports
|  | HIRDLS Accuracy & Knowledge Analysis |  | pdf | Alignment_Memo | 208KB | Submitted May 21, 2013
|  | Reduced Node Thermal Math Model |  | pdf | SP-HIR-138B | 175KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Comprehensive Optical Performance Anaylsis |  | pdf | TC-LOC-012 | 1.35MB | Submitted May 21, 2013
|  | Acceptance Screening of NonMetallics by Analysis |  | pdf | TC-LOC-376 | 13.6KB | Submitted May 21, 2013
|  | HIRDLS Verification of Settled Particles and NVR by Analysis |  | pdf | TC-LOC-377-378 | 14KB | Submitted May 21, 2013
|  | HIRDLS Structural Math Model |  | zip folder | TC-LOC-407 | 219KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Elevation Angle Jitter Analysis |  | pdf | TC-LOC-969 | 1.23MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | LOS Misalignment Lifetime Analysis |  | pdf | TC-LOC-1037 | 13.9KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Venting of HIRDLS Instrument During Ascent |  | pdf | TC-LOC-1213 | 845KB | Submitted May 21, 2013
|  | Assessment of HIRDLS Instrument In-field Spatial Characteristics |  | pdf | TC-LOC-1227 | 25.8KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Correlated Thermal Math Model |  | pdf | TC-LOC-1274 | 131KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Analysis of Radiometric Jitter Noise |  | pdf | TC-NCA-064 | 1.66MB | Submitted May 21, 2013
|  | Analysis of LOS pointing requirements |  | pdf | TC-OXF-039 | 41.9KB | Submitted May 21, 2013
|  | In-Flight Radiometric Accuracy |  | pdf | TC-OXF-046 | 285KB | Submitted May 21, 2013
|  | Derivation of ITS Scan Control Tables (Baseline Scan Patterns) |  | pdf | TC-OXF-185 | 45.2KB | Submitted May 21, 2013
|  | HIRDLS radiometric cross-calibration results - analysis of pre-launch calibration data |  | pdf | TC-OXF-417 | 58.5KB | Submitted May 21, 2013
|  | Optical System Throughput |  | xls | TC-RAL-037A | 4.3MB | Submitted May 21, 2013
|  | In-Band Optical System Throughput |  | pdf | TC-RAL-039 | 134KB | Submitted May 21, 2013
|  | Ghost Analysis Results |  | pdf | TC-RAL-047A | 94.8KB | Submitted May 21, 2013
|  | HIRDLS Pointing Accuracy and Knowledge Analysis |  | pdf | TR-HIR-2030 | 212KB | Submitted May 21, 2013
|  | Analysis Report for Radiometric Gain, Noise and Transfer Function |  | pdf | TR-LOC-1082 | 329KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Radiometric Gain Stability |  | pdf | TR-LOC-1083 | 340KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Horizontal Field of View |  | pdf | TR-LOC-1233 | 20.7KB | Submitted May 21, 2013 |  | ITAR restrictions apply
Test Reports
|  | HIRDLS Performance Verification Specification |  | pdf | SP-HIR-064 | 472KB | Submitted May 21, 2013
|  | HIRDLS Instrument Radiometric Test Program (draft only) |  | pdf | TC-LOC-017 | 58.5KB | Submitted May 21, 2013
|  | Stability of Radiometric Test Sources |  | pdf | TC-LOC-073 | 46KB | Submitted May 21, 2013
|  | HIRDLS Final Survival Power Numbers |  | pdf | TC-LOC-873 | 13.3KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Performance Verification Plan |  | pdf | TP-HIR-008D | 1.41MB | Submitted May 21, 2013
|  | SAIL Software Acceptance Test Report |  | pdf | TR-LOC-0957C | 545KB | Submitted May 21, 2013
|  | HIRDLS Instrument Level Vibe Test Report |  | pdf | TR-LOC-0988 | 2.19MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument EMI /EMC Test Reports |  | pdf | TR-LOC-1010 | 198MB | Submitted May 21, 2013
|  | STH to OBA cube alignment (shoot #2) |  | pdf | TR-LOC-1022 | 131KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Vibration Test |  | pdf | TR-LOC-1025 | 104MB | Submitted May 21, 2013
|  | Instrument Electrical Verification Test Report |  | pdf | TR-LOC-1052 | 185KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Mass Properties Report |  | pdf | TR-LOC-1057 | 16.7KB | Submitted May 21, 2013
|  | Thermal Vac/Thermal Balance Test Report |  | pdf | TR-LOC-1058 | 1.34MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Comprehensive Performance Test (CPT) Report |  | pdf | TR-LOC-1059 | 3.79MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Radiometric Gain Test Report |  | pdf | TR-LOC-1060 | 452KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Vertical Field of View and Response Test Report |  | pdf | TR-LOC-1062 | 1.02MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Out-of-Field Test Report |  | pdf | TR-LOC-1063 | 547KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Scan Dependent Angle Radiometric Effects Test Report |  | pdf | TR-LOC-1064 | 759KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Radiometric End-to-End Radiometric Noise Test Report |  | pdf | TR-LOC-1065 | 397KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Limited Performance Test Report |  | pdf | TR-LOC-1069 | 33.3MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument Bench Acceptance Test Pre-Ship Test Report |  | pdf | TR-LOC-1075 | 529KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Out-of-Field Test Report |  | pdf | TR-LOC-1210 | 308KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument LOS Vector Projected on Instr Alignment Cube, Summary Report (Draft only) |  | pdf | TR-LOC-1276 | 30.3KB | Submitted May 21, 2013 |  | ITAR restrictions apply
Critical Parameters/Data
|  | Command & Telemetry Handbook |  | pdf file | SP-HIR-103 | 3.25MB | Submitted May 21, 2013
|  | HIRDLS Instrument Test and Operational Constraints |  | pdf file | SP-HIR-366 | 83.7KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Instrument and Flight Software User Guide |  | pdf | SW-HIR-1072B | 624KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | HIRDLS Instr & Flight SW User Guide Supporting Information | various | SW-HIR-1072.zip | 7.72MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Science Algorithm Implementation Language (SAIL) Maintenance Manual |  | pdf | SW-LOC-0112 | 27.3KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | CLOAD Creation Untility Users Guide |  | pdf | SW-LOC-1219A | 49.8KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | CLOAD Programs and Documentation |  | zip folder | SW-LOC-1244 | 506KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Database Ingest Utility Users Guide |  | pdf | SW-LOC-1245 | 48.4KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | SAIL |  | pdf | SW-LOC-1346 | 98.8MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Radiometric Calibration Algorithms |  | pdf | SW-OXF-190B | 118KB | Submitted May 21, 2013
|  | Standards and Conventions for post launch SAIL tasks |  | pdf file | SW-OXF-287 | 259KB | Submitted May 21, 2013
|  | States & Modes Definitions |  | pdf | TC-LOC-172 | 15.1KB | Submitted May 21, 2013
|  | HIRDLS Autonomous Fault Management |  | pdf | TC-LOC-0212 | 15.7MB | Submitted May 21, 2013
|  | Collected channel transmittance data for optical system components |  | pdf | TC-LOC-0473 | 76.4KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Engineering Telemetry Conversion Reference Map |  | pdf | TC-LOC-759A | 37KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Engineering telemetry Conversion Coefficients |  | xls | TC-LOC-890 | 42.5KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Temperature Sensor Site Map |  | xls | TC-LOC-891 | 70KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Critical Parameter Trend Data |  | pdf file | TC-LOC-1097 | 393MB | Submitted May 21, 2013 |  | Lockheed proprietary
|  | Extraction and Conversion of HIRDLS Encoder Data |  | pdf | TC-LOC-1465 | 85.8KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Science Modes & Scanning Commands Sequence Doc |  | pdf | TC-NCA-062B | 3.05MB | Submitted May 21, 2013
|  | Spectral Response Data Files |  | pdf | TC-NCA-082 | 56.8KB | Submitted May 21, 2013
|  | Curtis-Godson Transmittance Tables |  | pdf | TC-NCA-083 | 65.8KB | Submitted May 21, 2013
|  | Signal channel dynamic range, gain settings and A to D conversion |  | pdf | TC-OXF-72 | 15.2KB | Submitted May 21, 2013
Other Documents
|  | Instrument Contaimination Control Plan |  | pdf | PA-HIR-006 | 905KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Instrument Operations Hazard Analyses |  | pdf | PA-LOC-272 | 185KB | Submitted May 21, 2013
|  | Instrument Safety Compliance Data Package |  | pdf | PA-LOC-1040A | 475KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS System Reliability Analysis |  | pdf | TC-LOC-0505 | 27.7KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | System FMEA |  | pdf | TC-LOC-0536 | 22.7KB | Submitted May 21, 2013 |  | ITAR restrictions apply
EM DATA PACKAGE
|  | HIRDLS Engineering Model Instrument Data Package |  | pdf | TC-HIR-367 | 11.3MB | Submitted May 21, 2013 |  | ITAR restrictions apply
MAJOR PROGRAM REVIEWS
Preliminary Design Review (PDR) Package
|  |  | PDR - Presentation | pdf | PDR-presentation | 119MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | PDR - CDRL package | pdf | PDR-CDRL_package | 23.2MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | PDR - Request For Action (RFA) responses | pdf | PDR-RFA_responses | 667KB | Submitted May 21, 2013
Critical Design Review (CDR) Package
|  |  | CDR - presentation package | pdf | CDR-presentation | 33.8MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | CDR - CDRL package | pdf | CDR-CDRL_package | 42.9MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | CDR - Request For Action (RFA) responses | pdf | CDR-RFA_responses | 290KB | Submitted May 21, 2013
Pre-Environmental Review (PER) Package
|  |  | PER - presentation package | pdf | PER-presentation | 20.1MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | PER - Request For Action (RFA) responses | pdf | PER-RFA_responses | 2.7MB | Submitted May 21, 2013 |  | ITAR restrictions apply
Pre-Ship review (PSR) Package (after I&T at Lockheed)
|  |  | PSR - presentation package | pdf | PSR-presentation | 110MB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  |  | PSR - Request For Action (RFA) responses | pdf | PM-LOC-1092-09A | 20.1KB | Submitted May 21, 2013 |  | ITAR restrictions apply
Delta Pre-Ship review (DPSR) Package (after calibration at Oxford)
|  |  | DPSR - presentation package | pdf | DPSR-presentation | 5.88MB | Submitted May 21, 2013
|  |  | DPSR - Request For Action (RFA) responses | pdf | DPSR-RFA_responses | 210KB | Submitted May 21, 2013
SUPPLIER DOCUMENTS AND REPORTS (additional documents not included in supplier's EIDP or in above list)
|  | Optical Tolerance Budget |  | pdf | TC-LOC-0140 | 212KB | Submitted May 21, 2013
|  | Derivation of Scanner Control Algorithms |  | pdf | TC-LOC-0142 | 76.1KB | Submitted May 21, 2013
|  | Derivation of Throughput Requirements for SSG-Assembly |  | zip | TC-LOC-0153 | 56.4KB | Submitted May 21, 2013
|  | FIR Filter Timing Test |  | pdf | TC-LOC-0201 | 10.9KB | Submitted May 21, 2013
|  | Line-of-Sight (LOS) Sensitivities |  | pdf | TC-LOC-322a | 716KB | Submitted May 21, 2013
|  | Implementation of scanner control algorithms |  | pdf | TC-LOC-353C | 260KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Traceability of focal-plane temperature telemetry conversion |  | pdf | TC-LOC-489 | 923KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Over-Temperature Fault Management Set Point Analysis |  | pdf | TC-LOC-940A | 24.1KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Vertical Resolution Study for HIRDLS |  | pdf | TC-OXF-007 | 1.58MB | Submitted May 21, 2013
|  | Signal to Noise Calculations |  | pdf | TC-OXF-016 | 663KB | Submitted May 21, 2013
|  | Angular Calibration of Gimbal Mirror |  | pdf | TC-OXF-022 | 565KB | Submitted May 21, 2013
|  | Signal to noise ratio performance of synchronous sampling as a method of demodulation |  | pdf | TC-OXF-052 | 705KB | Submitted May 21, 2013
|  | Analysis of the Impact of the Encoder Nonlinearity on the Relative Knowledge of Elevation |  | pdf | TR-LOC-711A | 940KB | Submitted May 21, 2013
|  | An Investigation of the Dependence of the Relative Knowledge of Elevation on Azimuth Position. |  | pdf | TR-LOC-712 | 1.2MB | Submitted May 21, 2013 |  | ITAR restrictions apply
POST LAUNCH REPORTS
|  | HIRDLS On-Orbit Anomaly Final Report |  | zip folder | PM-LOC-1497A | 12.6MB | Submitted May 21, 2013
|  | HIRDLS Venting Review |  | pdf | TC-LOC-1505 | 344KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | Analyses of HIRDLS Contam Closeout Blanket Response to Depressurization During Ascent |  | pdf | TC-LOC-1506 | 308KB | Submitted May 21, 2013 |  | ITAR restrictions apply
|  | HIRDLS Contamination Closeout Failure Investigation Final Report |  | pdf | TC-LOC-1507 | 4.92MB | Submitted May 21, 2013 |  | ITAR restrictions apply
3.1.2 | Preflight/Pre-Operational Calibration Data
REQUIREMENTS/SPECIFICATIONS
|  | Radiometric Calibration Budget for the High Resolution Dynamics Limb Sounder |  | pdf | SC-HIR-1892 | 2.02MB | Submitted Feb 21, 2013
|  | Fiducial Atmospheric Radiance Profiles |  | pdf | SP-HIR-090A | 146KB | Submitted Feb 21, 2013
|  | Pre-launch Calibration Requirements |  | pdf | SP-HIR-2031 | 88.5KB | Submitted Feb 21, 2013
|  | Monochromator Parameters for Pre-launch Calibration |  | pdf | SP-OXF-277b | 175KB | Submitted Feb 21, 2013
|  | Instrument Calibration Facility Requirements |  | pdf | TC-HIR-051 | 7.02MB | Submitted Feb 21, 2013
|  | Radiometric Calibration Parameters |  | pdf | TC-HIR-1681 | 12KB | Submitted Feb 21, 2013
| CALIBRATION PLANS AND PROCEDURES | [5 empty] | Submitted Feb 21, 2013
|  | SAIL (folder of tasks used during calibration) |  | various, as submitted by OXFORD | SAIL | 596KB | Submitted Feb 21, 2013
|  | SEG_Procedures (folder of procedures used during calibration) |  | various, as submitted by OXFORD | seg_procedures | 38MB | Submitted Feb 21, 2013
|  | A Method for Determining and Applying the Effects of Out-Of-Field Response in Radiometric Calibration |  | pdf | TC-UCB-076 | 24.2KB | Submitted Feb 21, 2013
|  | Pre-launch Calibration Plan |  | pdf | TP-HIR-007B | 212KB | Submitted Feb 21, 2013
|  | Pre-launch Calibration Procedures |  | pdf | TP-OXF-217 | 169KB | Submitted Feb 21, 2013
| CALIBRATION DATA | [5 empty] | Submitted Feb 21, 2013
|  | FOV Package-1 |  | various, as submitted by OXFORD | fov_package_1 | 7.62MB | Submitted Feb 21, 2013
|  | FOV Package-2 |  | various, as submitted by OXFORD | fov_package_2 | 38.2KB | Submitted Feb 21, 2013
|  | FOV Package-3 |  | various, as submitted by OXFORD | fov_package_3 | 22.6MB | Submitted Feb 21, 2013
|  | Test Data (folder of pre-launch calibration data submitted by Oxford Univeristy) |  | various, as submitted by OXFORD | Test_Data | 35.4GB | Submitted Feb 21, 2013
|  | Test Logs (folder of test activities) |  | various, as submitted by OXFORD | Test_Logs | 4.92MB | Submitted Feb 21, 2013
| CALIBRATION RESULTS AND REPORTS | [5 empty] | Submitted Feb 21, 2013
|  | Field-of-View (folder of results & reports submitted by Oxford University) |  | various, as submitted by OXFORD | fov | 57MB | Submitted Feb 21, 2013
|  | Out-of-Field (folder of results & reports submitted by Oxford University) |  | various, as submitted by OXFORD | oof | 96MB | Submitted Feb 21, 2013
|  | Radiometric Calibration (folder of results & reports submitted by Oxford University) |  | various, as submitted by OXFORD | radcal | 9.73MB | Submitted Feb 21, 2013
|  | Spectral Calibration (folder of results & reports submitted by Oxford University) |  | various, as submitted by OXFORD | spectral | 24.3MB | Submitted Feb 21, 2013
|  | Detector Response vs. Focal Plane Assembly (FPA) Drift |  | pdf | Det_response_vs_FPA_drift | 176KB | Submitted Feb 21, 2013
|  | HIRDLS Calibration Coefficients for Science Processing |  | pdf | SC-HIR-1505 | 48.8KB | Submitted Feb 21, 2013
|  | Spectral Characterization of the HIRDLS Flight Instrument From Pre-launch Cal Data |  | pdf | SC-HIR-1997 | 3.55MB | Submitted Feb 21, 2013
|  | Radiometric Calibration Algorithms |  | pdf | SW-OXF-190b | 118KB | Submitted Feb 21, 2013
|  | PRT Temp Sensor Vendor Calibration Charts |  | pdf | TC-LOC-937 | 3.47MB | Submitted Feb 21, 2013
|  | RADMETAC Budget Description |  | pdf | TC-OXF-097a | 224KB | Submitted Feb 21, 2013
|  | Radiometric Interference - Summary of Findings |  | pdf | TR-HIR-2034 | 722KB | Submitted Feb 21, 2013
|  | Proto-flight Midel Scanner Elevation Encoder Calibration Data Analysis |  | pdf | TR-LOC-868 | 2.99MB | Submitted Feb 21, 2013
|  | Proto-flight Midel Scanner Asimuth Encoder Calibration Data Analysis |  | pdf | TR-LOC-869 | 912KB | Submitted Feb 21, 2013 |  | ITAR restrictions apply
|  | Proto-flight Model Scanner Wobble Sensor Calibration Analysis |  | pdf | TR-LOC-877A | 966KB | Submitted Feb 21, 2013 |  | ITAR restrictions apply
SUPPLIER DOCUMENTS AND REPORTS
|  | Tools & References (folder containing add'l info from OXFORD, incl drawings & photos) |  | various, as submitted by OXFORD | Tools_References | 26.8MB | Submitted Feb 21, 2013
|  | Radiometric Calibration Algorithms |  | pdf | SW-OXF-190b | 118KB | Submitted Feb 21, 2013
|  | Scan Mirror Calibration: Interferometer Theory and error budget |  | pdf | TC-OXF-057 | 1.01MB | Submitted Feb 21, 2013
Section 3.2 | Science Data Products (Data)
3.2.1 | Raw Data and Derived Products
|  | L0 data |  | Already at the DISC |  |  | N/A |  |  | No action needed
|  | Orbit, attitude, ephemeris data |  | Already at the DISC |  |  | N/A |  |  | No action needed
HIRDLS1 (Calibrated Geolocated Radiances)
|  |  | V3 |  |  |  | Submitted Mar 12, 2013
|  |  | V4 |  |  |  | Submitted Mar 12, 2013
|  |  | V5 |  |  |  | Submitted Mar 12, 2013
|  |  | V6 |  |  |  | Submitted Mar 12, 2013
|  |  | V7 |  |  |  | Submitted Dec-2012
HIRDLS1C (Calibrated Geolocated Radiances Corrected for Obstruction)
|  |  | V3 |  |  |  | Submitted Mar 12, 2013
|  |  | V4 |  |  |  | Submitted Mar 12, 2013
|  |  | V5 |  |  |  | Submitted Mar 12, 2013
|  |  | V6 |  |  |  | Submitted Mar 12, 2013
|  |  | V7 |  |  |  | Submitted Dec-2012
HIRDLS1R (Calibrated Geolocated Radiances Corrected for Obstruction and Vertically Gridded)
|  |  | V3 |  |  |  | Submitted Mar 12, 2013
|  |  | V4 |  |  |  | Submitted Mar 12, 2013
|  |  | V5 |  |  |  | Submitted Mar 12, 2013
|  |  | V6 |  |  |  | Submitted Mar 12, 2013
|  |  | V7 |  |  |  | Submitted Dec-2012
HIRDLS2 (Geophysical Parameters)
|  |  | V3 |  |  |  | Submitted Apr 10, 2013
|  |  | V4 |  |  |  | Submitted Apr 10, 2013
|  |  | V5 |  |  |  | Already at DISC
|  |  | V6 |  |  |  | Already at DISC
|  |  | V7 (provide HIRDLS2 and HIRDLS2ALL for final version) |  |  |  | Delivered HIRDLS2 Dec 2012, HIRDLS2ALL Jun2013 |  |  | Need to submit HIRDLS2ALL for archiving only
|  | H3IWC Level 3 Ice Water Content (combined product with MLS) |  |  |  |  | Delivered March 15, 2013
|  | H3ZFC<species> (zonal fourier coefficients for species) - V7 only |  |  |  |  | Delivered May 6, 2013
|  | H3 Strat cloumns - V7 |  |  |  |  | Delivered May 7, 2013
3.2.2 | Metadata
|  | Our metadata are included in the data product files |  |  |  |  | N/A
SECTION 3.3 | Product Documentation
3.3.1 | Product Team
|  | HIRDLS Team Contact Information |  | pdf | N/A | 30.5KB | Submitted Jan 23, 2013
3.3.2 | Product Requirements and Designs
|  | HIRDLS Science Data Management Plan |  | pdf | SC-HIR-135 | 111KB | Submitted Dec 20, 2012
|  | HIRDLS SIPS Processor Requirements |  | pdf | SP-UCB-067 | 35.3KB | Submitted Dec 20, 2012
|  | HIRDLS High Level Data Flow |  | pdf | SW-HIR-2018 | 318KB | Submitted Dec 20, 2012
|  | HIRDLS Level 2 Data Flow |  | pdf | SW-HIR-2019 | 313KB | Submitted Dec 20, 2012
|  | HIRDLS Level 3 Data Flow |  | pdf | SW-HIR-2020 | 150KB | Submitted Dec 20, 2012
|  | The HIRDLS SIPS Operations Manual |  | pdf | SW-UCB-087 | 55.7KB | Submitted Dec 20, 2012
|  | The HIRLDS Science Investigator-led Processing System (SIPS) |  | pdf | TC-UCB-060 | 869KB | Submitted Dec 20, 2012
3.3.3 | Processing and Algorithm Versions History
|  | Processing Version History |  | pdf | SW-HIR-2029 | 32.3KB | Submitted Jan 25, 2013
3.3.4 | Product Generation Algorithms
|  | L1 ATBD |  | pdf | SW-HIR-168a | 513KB | Submitted Jun 26, 2013
|  | L1 ATBD - Post launch update |  | pdf | SW-HIR-2046 | 3.9MB | Submitted Jun 18, 2013
|  | Level 2 ATBD |  | pdf | SW-HIR-339 | 2.9MB | Submitted Jun 18, 2013
|  | Level 2 ATBD Update |  | pdf documents | SW-HIR-2047 | 458KB | Submitted Jun 18, 2013
3.3.5 | Product Quality
|  | Data Description and Quality Documents |  |  | SC-HIR-1511
|  |  | Version 3 | pdf | HIRDLS-DQD_V3 | 3.03MB | Delivered with data version. Put on ftp server for archiving Dec 20, 2012
|  |  | Version 4 | pdf | HIRDLS-DQD_V4 | 4.43MB | Delivered with data version. Put on ftp server for archiving Dec 20, 2012
|  |  | Version 5 | pdf | HIRLDS-DQD_V5 | 4.26MB | Delivered with data version. Put on ftp server for archiving Dec 20, 2012
|  |  | Version 6 | pdf | HIRLDS-DQD_V6 | 51.7MB | Delivered with data version. Put on ftp server for archiving Dec 20, 2012
|  |  | Version 7 | pdf | HIRLDS-DQD_V7 | 20.8MB | Updated version (SC-HIR-1511L)
3.3.6 | Product Application
|  | Spreadsheet listing publications using HIRDLS data |  | pdf | All_HIRDLS_Papers_26June2013 | 52.9KB | Submitted Jun 27, 2013 | Various journals | Public | Citiations are given for published papers
SECTION 3.4 | Mission Calibration
3.4.1 | Calibration Method
|  | Flight Operations Concept Document |  | pdf | OP-HIR-167 | 34KB | Submitted April 11, 2013
|  | Derivation of HIRDLS On-Orbit Calibration |  | pdf | SC-HIR-2045 | 166KB | Submitted April 11, 2013
|  | HIRDLS On-Orbit Engineering & Housekeeping Data Monitoring |  | pdf | SP-HIR-377B | 155KB | Submitted April 11, 2013
|  | Scan Table Interpolation Algorithms |  | pdf | SW-LOC-293 | 63.5KB | Submitted April 11, 2013
|  | Mirror Scans and Scan Table Entries |  | pdf | SW-LOC-295 | 81.5KB | Submitted April 11, 2013
|  | HIRDLS Pitch-up Maneuvers Overview |  | pdf | TC-HIR-2022 | 131KB | Submitted April 11, 2013
|  | HIRDLS Pitch-up Maneuvers History (dates, times) |  | pdf | TC-HIR-2023 | 90.1KB | Submitted April 11, 2013
|  | Scan Tables Descriptions |  | pdf | TC-HIR-2025 | 138KB | Submitted April 11, 2013
|  | Scan ID Summary (times when Scan ID changed) |  | pdf | TC-HIR-2028 | 88.6KB | Submitted April 11, 2013
3.4.2 | Calibration Data
|  | HIRDLS calibration data is part of the L1C file |  |  | N/A
|  | HIRDLS Mission Calendar (log of HIRDLS ops - Scan Tables used, maneuvers executed) |  | pdf | HIRDLSMissionCalendar | 1.7MB | Submitted Jan 23, 2013
SECTION 3.5 | Science Data Product Software
SOURCE CODE
|  | Level 1PP Source Codes (For versions 3-7) |  | gzipped tar files |  |  | Submitted Apr 3, 2013
|  | Level 1 Source Codes (For versions 3 - 7) |  | gzipped tar files |  |  | Submitted Apr 3, 2013
|  | Level 2 Source Codes (For versions 3-7) |  | gzipped tar files Custom C++, FORTRAN, IDL and JAVA; uses HDF5 libraries |  |  | Submitted May 28, 2013
|  | Level 3 Source Code (For version 7 only, L3 was not produced for earlier versions) |  | gzipped tar files |  |  | Submitted June 3, 2013
|  | Forward Model Source Code and Documentation |  | tar file |  |  | Submitted Apr 3, 2013
DOCUMENTATION-L1
|  | The Requirements of the HIRDLS Level 0 - Level 1 Processor (L1X) |  | pdf | SW-HIR-2000 | 309KB | Submitted Dec 20, 2012
|  | The Requirements of the HIRDLS Level 1 Correction Processor (L1C) |  | pdf | SW-HIR-2001 | 245KB | Submitted Dec 20, 2012
|  | The Requirements of the HIRDLS Level 2 Preprocessor (L2PP) |  | pdf | SW-HIR-2002 | 288KB | Submitted Dec 20, 2012
|  | The Architecture of the HIRDLS Level 0 - Level 1 Processor (L1X) |  | pdf | SW-HIR-2003 | 291KB | Submitted Dec 20, 2012
|  | The Architecture of the HIRDLS Level 1 Correction Processor (L1C) |  | pdf | SW-HIR-2004 | 276KB | Submitted Dec 20, 2012
|  | The Architecture of the HIRDLS Level 2 Preprocessor (L2PP) |  | pdf | SW-HIR-2005 | 274KB | Submitted Dec 20, 2012
|  | The Design of the HIRDLS Level 0 - Level 1 Processor (L1X) |  | pdf | SW-HIR-2006 | 2.75MB | Submitted Dec 20, 2012
|  | The Design of the HIRDLS Level 1 Correction Processor (L1C) |  | pdf | SW-HIR-2007 | 1.88MB | Submitted Dec 20, 2012
|  | The Design of the HIRDLS Level 2 Preprocessor (L2PP) |  | pdf | SW-HIR-2008 | 1.88MB | Submitted Dec 20, 2012
|  | The User's Guide of the HIRDLS Level 0 - Level 1 Processor (L1X) |  | pdf | SW-HIR-2009 | 299KB | Submitted Dec 20, 2012
|  | The User's Guide of the HIRDLS Level 1 Correction Processor (L1C) |  | pdf | SW-HIR-2010 | 295KB | Submitted Dec 20, 2012
|  | The User's Guide of the HIRDLS Level 2 Preprocessor (L2PP) |  | pdf | SW-HIR-2011 | 288KB | Submitted Dec 20, 2012
DOCUMENTATION-L2
|  | H2BOP (Build Output) Overview |  | pdf | SW-HIR-2012 | 294KB | Submitted Dec 20, 2012
|  | H2CLP_Driver (Collocate) |  | pdf | SW-HIR-2013 | 193KB | Submitted Dec 20, 2012
|  | H2GMC_Driver (GMAO data collocator) |  | pdf | SW-HIR-2014 | 181KB | Submitted Dec 20, 2012
|  | H2LSP_Main (Line of sight weighting) |  | pdf | SW-HIR-2015 | 199KB | Submitted Dec 20, 2012
|  | HIRDLS Level 2 Processor |  | pdf | SW-HIR-2016 | 182KB | Submitted Dec 20, 2012
|  | H2RTP_Driver (Retrieval wrapper) |  | pdf | SW-HIR-2017 | 253KB | Submitted Dec 20, 2012
|  | SWATH Module (reading/writing HDF-EOS5 Swath formatted files) |  | pdf | SW-HIR-2021 | 464KB | Submitted Dec 20, 2012
|  | Level 2 Processor General Development Strategy & Notes on Running Jobs |  | pdf | SW-HIR-2024 | 772KB | Submitted Dec 20, 2012
DOCUMENTATION-L3
|  | Level 3 Documentation (For version 7 only, L3 was not produced for earlier versions) |  | pdf | SW-HIR-2048 | 145KB | Submittec Jun 18, 2013
SECTION 3.6 | Science Data Product Algorithm Inputs
|  | Effect of Using CLCMLS Data for Contaminants in the Retrievals |  | pdf | TC-HIR-1962 | 1.44MB | Submitted Apr 29, 2013
SECTION 3.7 | Science Data Product Validation
|  | Science Data Product Validation Plan |  | pdf | SC-HIR-022 | 7MB | Submitted Jun 27, 2013
|  | Validation papers of HIRDLS data products |  | pdf | HIRDLS_Validation_Papers_26June2013 | 18.7KB | Submitted Jun 27, 2013 | Various journals | Public | Citiations are given for published papers
SECTION 3.8 | Science Data Software Tools
|  | OrbitPlot - Source Code and brief description |  |  |  |  | Submitted Apr 26, 2013
SECTION 3.9 | Deliverables Checklist
|  | List of data and documents submitted for archiving. |  | pdf | N/A |  | Submitted Jun 27, 2013