## Status-September4,02
UARS Data Archive Status (9/4/02)
Instrument | Data Level | Sub - Type | UARSDB/UCSS/INGRES/FileTek-MSS |  |  |  | Volume to Archive |  | USDSPCx |  |  |  | DIRAC |  |  |  | NOTES
|  |  | UARS Days |  | Total # of Files | Space (GB) | Total # of Files | Space (GB) | UARS Days |  | Total # of Files | Space (GB) | UARS Days |  | Total # of Files | Space (GB)
|  |  | Start | End |  |  |  |  | Start | End |  |  | Start | End
Observatory | L0 | OBC | 4 | 3672 | 3662 | 59.77 | 3662 | 59.77 |  |  | 3662 | 59.69 |  |  | 3662 | 59.69
|  | ENGINEERING | 4 | 3672 | 3662 | 34.3 | 3662 | 34.3 |  |  | 3662 | 34.22 |  |  | 3662 | 34.22
|  | SPACECRAFT | 4 | 3672 | 3662 | 178.87 | 3662 | 178.87 |  |  | 3662 | 178.69 |  |  | 3662 | 178.69
|  | ORB_DEF | 4 | 3765 | 3730 | 0.18 | 3730 | 0.18 |  |  | 3730 | 0.18 |  |  | 3730 | 0.18
ORB_PRED
|  | ATT_SSPP | 4 | 3672 | 3662 | 6.03 | 3662 | 6.03 |  |  | 3656 | 6.04 |  |  | 3656 | 6.04
|  | ATT_EXTR | 4 | 3672 | 3662 | 6.04 | 3662 | 6.04 |  |  | 3656 | 6.05 |  |  | 3656 | 6.05
|  | ATT_DEFNSC | 29 | 812 | 13 | 0.02 | 13 | 0.02 |  |  | 13 | 0.02 |  |  | 13 | 0.02
|  | QUALITY | 4 | 3672 | 3662 | 10.58 | 3662 | 10.58 |  |  | 3662 | 10.5 |  |  | 3662 | 10.5
CLAES | PISW |  |  |  | 511 | 0.04
| CALIBRATION |  |  |  | 63 | 0.0032617 | 599 | 18.1 | 4 | 602 | 63 | 0.003 | 4 | 602 | 63 | 0.003 | Complete
| L0 |  | 4 | 602 | 599 | 18.14 | 599 | 18.1 | 4 | 602 | 599 | 18.1 | 4 | 602 | 599 | 18.1
| L1 |  | 40 | 602 | 460 | 6.65 | 460 | 6.62 | 40 | 602 | 460 | 6.62 | 40 | 602 | 460 | 6.63 | Complete
| L2 |  | 40 | 602 | 460 | 5.58 | 460 | 5.56 | 40 | 602 | 460 | 5.56 | 40 | 602 | 460 | 5.57 | Complete
ISAMS | PISW |  |  |  | 840 | 0.01041
| CALIBRATION |  |  |  | 430 | 0.075811 |  |  |  |  | 430 | 0.08 | 4 | 602 | 430 | 0.08
| L0 |  | 4 | 322 | 319 | 3.24 | 319 | 3.24 | 17 | 190 | 319 | 3.23 |  |  | 319 | 3.23 | (4-16, 37-53) 30 days missing (from rehost!)
| L1 | DATA | 4 | 322 | 204 | 3.79 | 204 | 3.79 | 15 | 92 | 182 | 3.36 |  |  | 182 | 3.38
|  | LOG | 4 | 322 | 204 | 0.01
| L2 | 00PRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 00WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 10PRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 10WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 10X | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | 11A | 15 | 322 | 180 | 0.05 | 180 | 0.05 |  |  | 180 | 0.04 |  |  | 180 | 0.04
|  | 11X | 15 | 322 | 179 | 0.1 | 179 | 0.1 |  |  | 179 | 0.09 |  |  | 179 | 0.09
|  | 121X | 15 | 322 | 185 | 0.1 | 185 | 0.1 |  |  | 182 | 0.09 |  |  | 182 | 0.09
|  | 16X | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | 20PRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 20WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 30PRAD | 15 | 322 | 185 | 0.2
|  | 30WRAD | 15 | 322 | 185 | 0.2
|  | 31PRAD | 15 | 322 | 185 | 0.2
|  | 31WRAD | 15 | 322 | 185 | 0.2
|  | 32WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 33WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 40PRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 40WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 45X | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | 50PRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 50WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 53A | 15 | 322 | 180 | 0.08 | 180 | 0.08 |  |  | 180 | 0.08 |  |  | 180 | 0.08
|  | 53X | 15 | 322 | 182 | 0.1 | 182 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | 60PRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 181 | 0.28 |  |  | 181 | 0.28 |  | Missing day 256
|  | 60WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 62X | 15 | 322 | 182 | 0.14 | 182 | 0.14 |  |  | 181 | 0.13 |  |  | 181 | 0.13 |  | Missing day 25
|  | 68X | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.092285 |  |  | 180 | 0.092285
|  | 70PRAD | 15 | 322 | 185 | 0.2
|  | 70WRAD | 15 | 322 | 185 | 0.2
|  | 71PRAD | 15 | 322 | 185 | 0.2
|  | 71WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 72WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 73WRAD | 15 | 322 | 185 | 0.29 | 185 | 0.29 |  |  | 182 | 0.28 |  |  | 182 | 0.28
|  | 74X | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | 78X | 15 | 322 | 181 | 0.1 | 181 | 0.1 |  |  | 181 | 0.09 |  |  | 181 | 0.09
|  | 81X | 15 | 322 | 179 | 0.1 | 179 | 0.1 |  |  | 179 | 0.09 |  |  | 179 | 0.09
|  | AERO10P0 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.092285 |  |  | 180 | 0.092285
|  | AERO11P4 | 15 | 322 | 179 | 0.1 | 179 | 0.1 |  |  | 177 | 0.09 |  |  | 177 | 0.09 |  | Missing days 199 & 255
|  | AERO12P1 | 15 | 322 | 185 | 0.1 | 185 | 0.1 |  |  | 182 | 0.09 |  |  | 182 | 0.09
|  | AERO16P3 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | AERO4P51 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | AERO5P28 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | AERO6P23 | 15 | 322 | 182 | 0.14 | 182 | 0.14 |  |  | 181 | 0.13184 |  |  | 181 | 0.13184 |  | Missing day 120
|  | AERO6P76 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | AERO7P43 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | AERO7P81 | 15 | 322 | 180 | 0.1 | 180 | 0.1 |  |  | 180 | 0.09 |  |  | 180 | 0.09
|  | AERO8P09 | 15 | 322 | 179 | 0.1 | 179 | 0.1 |  |  | 179 | 0.09 |  |  | 179 | 0.09
|  | CH4 | 15 | 322 | 185 | 0.1 | 185 | 0.1 |  |  | 182 | 0.09 |  |  | 182 | 0.09
|  | CO | 15 | 322 | 185 | 0.11 | 185 | 0.11 |  |  | 182 | 0.1 |  |  | 182 | 0.1
|  | H2O | 15 | 322 | 185 | 0.06 | 185 | 0.06 |  |  | 182 | 0.05 |  |  | 182 | 0.05
|  | HNO3 | 15 | 322 | 185 | 0.05 | 185 | 0.05 |  |  | 180 | 0.05 |  |  | 180 | 0.05 |  | Missing day 22
|  | N2O | 15 | 322 | 185 | 0.07 | 185 | 0.07 |  |  | 182 | 0.06 |  |  | 182 | 0.06
|  | N2O5 | 15 | 322 | 182 | 0.04 | 182 | 0.04 |  |  | 182 | 0.03 |  |  | 182 | 0.03
|  | NO | 15 | 322 | 182 | 0.21 | 182 | 0.21 |  |  | 181 | 0.21 |  |  | 181 | 0.21
|  | NO2 | 15 | 322 | 185 | 0.14 | 185 | 0.14 |  |  | 182 | 0.13 |  |  | 182 | 0.13
|  | O3 | 15 | 322 | 185 | 0.06 | 185 | 0.06 |  |  | 182 | 0.05 |  |  | 182 | 0.05
|  | PRES | 15 | 322 | 185 | 0.14 | 185 | 0.14 |  |  | 182 | 0.14 |  |  | 182 | 0.14
|  | TEMP | 15 | 322 | 185 | 0.14 | 185 | 0.14 |  |  | 182 | 0.14 |  |  | 182 | 0.14
MLS | PISW |  |  |  | 318 | 0.018077
| CALIBRATION |  |  |  | 5371 | 11.08 | 3662 | 42.8 |  |  | 5369 | 10.62 |  |  | 5369 | 10.62
| L0 |  | 4 | 3672 | 3662 | 42.8 |  |  |  |  | 3002 | 37.72 |  |  | 3002 | 37.82
| L1 | LOG | 5 | 938 | 934 | 0.11
|  | DIAG | 5 | 3636 | 2984 | 30.49
|  | ENG | 5 | 3636 | 2984 | 5.79
|  | RAD | 5 | 3636 | 2984 | 53.19 | 2984 | 53.19 | 7 | 100 | 2982 | 52.9 |  |  | 2983 | 53.07 |  | Missing day 5
| L2 | ICE_SATURAT | 7 | 2876 | 1441 | 1.63
|  | L2OUT | 5 | 3636 | 1534 | 28.56 | 1540 | 28.56 | 7 | 3636 | 1529 | 26.7 |  |  | 1531 | 26.9 |  | Day 786 added from PC (re-verify!)
|  | MLS_LMFQ | 5 | 3636 | 1534 | 0.41
HALOE | PISW |  |  |  | 396 | 0.011631
| CALIBRATION |  |  |  | 5153 | 1.19 |  |  |  |  | 5153 | 1.19 | 4 | 602 | 5153 | 1.19
| L0 |  | 4 | 3672 | 3662 | 136.44 | 3662 | 136.44 | 4 | 586 | 2039 | 82.16 |  |  | 3662 | 136.3
| L1 | AVERAGE | 30 | 562 | 362 | 0.01
|  | BORESIGHT | 30 | 3615 | 209 | 0.2
|  | CALRISE | 30 | 1451 | 998 | 1.74
|  | CALSET | 30 | 1451 | 999 | 1.74
|  | COMMENTS | 30 | 1451 | 2639 | 0.18
|  | FOVTEST | 50 | 1062 | 22 | 0.0048
|  | GAINCAL | 31 | 3615 | 598 | 0.34
|  | GIMBALTEST | 71 | 709 | 15 | 0.00031
|  | HALOEOADATA | 30 | 3666 | 2639 | 0.02
|  | LOG | 30 | 562 | 362 | 0.02
|  | SLZPTIME | 30 | 3666 | 2663 | 0.18
|  | QC | 30 | 388 | 268 | 0.93
|  | SCANRISE | 30 | 3666 | 2657 | 9.34
|  | SCANSET | 30 | 3666 | 2659 | 8.9
|  | SPECIALTEST | 254 | 892 | 6 | 0.01
|  | STATUS | 30 | 3666 | 2639 | 0.18
|  | THERMALDRIFT | 30 | 710 | 467 | 0.01
|  | TRAKRISE | 30 | 3666 | 2657 | 7.02
|  | TRAKSET | 30 | 3666 | 2657 | 6.05
|  | FINAL | 30 | 3666 | 2636 | 13.31 | 2636 | 13.31 | 111 | 150 | 2635 | 13.23 |  |  | 2635 | 13.23
HRDI | PISW |  |  |  | 1185 | 0.022346
| CALIBRATION | MISC | 1 | 27 | 31 | 0.02 |  |  |  |  | 31 | 0.02 |  |  | 31 | 0.02
|  | AEO_2B | 79 | 2947 | 1056 | 0.34 |  |  |  |  | 1056 | 0.34 |  |  | 1056 | 0.34
|  | AERO_MAP | 27 | 1060 | 241 | 0.04 |  |  |  |  | 241 | 0.04 |  |  | 241 | 0.04
|  | AERO_MAP2 | 1 | 2947 | 1057 | 0.21 |  |  |  |  | 1057 | 0.21 |  |  | 1057 | 0.21
|  | PRES | 1 | 2947 | 2066 | 9.93 |  |  |  |  | 2066 | 9.93 |  |  | 2066 | 9.93
|  | UZONAV | 27 | 2947 | 1213 | 1.53 |  |  |  |  | 1213 | 1.53 |  |  | 1213 | 1.53
|  | VELO | 1 | 2947 | 2065 | 9.93 |  |  |  |  | 2065 | 9.93 |  |  | 2065 | 9.93
| L0 |  | 4 | 3672 | 3662 | 161.9 | 3662 | 161.9 |  |  | 2846 | 132.7 |  |  | 3662 | 161.76
| L1 | IPF | 17 | 701 | 677 | 1
|  | LOG | 17 | 3666 | 3639 | 0.43
|  | HCDF | 17 | 3666 | 3633 | 174.09 | 3633 | 174.09 | 17 | 85 | 2934 | 142.41 |  |  | 3588 | 171.66 |  | Days 2021 to 2064 need to be moved from /u4/mcb
| L2 | LOS | 50 | 2947 | 2104 | 13.23 | 2104 | 13.23 | 50 | 2947 | 2104 | 13.15 | 50 | 2947 | 2104 | 13.15 | Complete
|  | PROFILE | 50 | 2947 | 2104 | 6.32 | 2104 | 6.32 | 50 | 2947 | 1859 | 5.92 |  |  | 1734 | 5.7 | Get missing files
WINDII | PISW |  |  |  | 1053 | 0.025078
| CALIBRATION |  |  |  | 688 | 0.19 |  |  |  |  | 688 | 0.19 |  |  | 688 | 0.19
| L0 |  | 4 | 3672 | 3662 | 68.26 | 3662 | 68.26 |  |  | 3662 | 68.18 |  |  | 3662 | 68.18
| L1 |  | 20 | 2445 | 26058 | 173.85 | 26058 | 173.85 |  |  | 26058 | 173.85 |  |  | 26058 | 173.85
| L2 | AQ | 21 | 2445 | 1619 | 15.66 | 1619 | 15.66 | 21 | 500 | 1619 | 15.66 |  |  | 1619 | 15.66
|  | AQO2 | 180 | 592 | 68 | 0.0042 |  |  |  |  | 68 | 0.0042 |  |  | 68 | 0.0042
|  | CD | 21 | 2445 | 1619 | 1 | 1619 | 1 | 21 | 2445 | 1619 | 0.93 |  |  | 1619 | 0.93 | Missed 4 files
|  | DS | 21 | 2445 | 1619 | 0.63 |  |  |  |  | 1619 | 0.63 |  |  | 1619 | 0.63
|  | DSO2 | 54 | 2445 | 1616 | 0.17 |  |  |  |  | 1616 | 0.17 |  |  | 1616 | 0.17
|  | FD1 | 21 | 2445 | 1619 | 4.88 |  |  |  |  | 1619 | 4.88 |  |  | 1619 | 4.88
|  | FD1O2 | 54 | 2445 | 1616 | 0.33 |  |  |  |  | 1616 | 0.33 |  |  | 1616 | 0.33
|  | FD2 | 21 | 2445 | 1619 | 4.89 |  |  |  |  | 1619 | 4.89 |  |  | 1619 | 4.89
|  | FD2O2 | 54 | 2445 | 1616 | 0.33 |  |  |  |  | 1616 | 0.33 |  |  | 1616 | 0.33
|  | FDGO2 | 54 | 2445 | 1616 | 1.25 |  |  |  |  | 1616 | 1.25 |  |  | 1616 | 1.25
SOLSTICE | PISW |  |  |  | 557 | 0.021442
| CALIBRATION |  |  |  | 11560 | 19.62 | 3662 | 10.58 | 4 | 1660 | 11531 | 19.15 |  |  | 11531 | 19.15
| L1 | ENGDATA | 4 | 3672 | 3660 | 3.83 | [10 empty] | UCSS Database didn't returm an MSS name for SOLSTICE L1 Days 3668-3672
|  | SUMMARY | 10 | 3672 | 3555 | 0.25
|  | LOG | 4 | 3672 | 3660 | 0.38
| L0 |  | 4 | 3672 | 3662 | 10.58 | 3662 | 10.58 | 4 | 1660 | 1651 | 5.13 |  |  | 3379 | 9.62
| L1 | SOLAR | 10 | 3672 | 3554 | 6.19 | 3554 | 6.19 |  |  | 3545 | 6.05 |  |  | 3548 | 6.06
|  | STELLAR | 12 | 3666 | 3017 | 0.91 | 3017 | 0.91 |  |  | 3016 | 0.8 |  |  | 3017 | 0.8
| L2 | CWR | 22 | 2994 | 2856 | 0.2
|  | LINES | 22 | 2994 | 2867 | 0.34
|  | SOLAR | 22 | 2994 | 2867 | 14.67 | 2867 | 14.67 | 22 | 2339 | 2866 | 14.5 |  |  | 2867 | 14.55
|  | STELLAR | 32 | 2985 | 2485 | 1.67 | 2485 | 1.67 | 32 | 2985 | 2485 | 1.58 |  |  | 2485 | 1.58
SUSIM | PISW |  |  |  | 412 | 0.0049219
| CALIBRATION |  |  |  | 81 | 0.0036035 |  |  |  |  | 81 | 0.0036035 |  |  | 81 | 0.0036035
| L0 | SUSIMA | 4 | 3672 | 3662 | 34.3 | 3662 | 34.3 |  |  | 2287 | 23.15 |  |  | 3662 | 34.22
|  | SUSIMB | 4 | 3672 | 3662 | 34.3
| L1 | COMMAND | 14 | 3666 | 3393 | 0.24
|  | COND_SCANS | 122 | 146 | 8 | 0.001
|  | CURRENT | 7 | 3666 | 3463 | 0.25
|  | D2_SCANS | 30 | 3658 | 184 | 0.02
|  | DARK | 1 | 3666 | 3465 | 0.24
|  | DARK_ALL | 30 | 3666 | 3362 | 0.24
|  | DATABASE | 1 | 3666 | 3395 | 0.24
|  | DATABASE_UPD | 14 | 3666 | 2587 | 0.18
|  | DET_CAL | 23 | 3666 | 3332 | 0.36
|  | DET_IOP | 30 | 3666 | 3359 | 2.99
|  | DWELL_PROF | 30 | 3666 | 1170 | 0.17
|  | EXCEPT | 15 | 3666 | 3369 | 0.23
|  | EXPOSURE | 7 | 3666 | 3390 | 0.24
|  | FID_LINES | 30 | 3666 | 3358 | 0.24
|  | FID_NOFOV | 30 | 3666 | 3358 | 0.23
|  | LOG | 14 | 3666 | 3325 | 0.2
|  | OBSERVE | 14 | 3666 | 3393 | 0.24
|  | OCC_DWELL | 40 | 3003 | 710 | 0.14
|  | PHASE2_FID_L | 30 | 3666 | 3357 | 0.24
|  | PROGRAM | 1 | 3666 | 3395 | 0.65
|  | PROGRAM_UPD | 14 | 3656 | 212 | 0.01
|  | RAW_ACT | 23 | 3666 | 3370 | 3.88
|  | SOLAR_NOFOV | 30 | 3666 | 3359 | 1.23
|  | SOLAR_SCANS | 30 | 3666 | 3359 | 1.22 | 2763 | 1.07 |  |  | 2450 | 0.77 |  |  | 1640 | 0.49 |  | 1688 to 2578 missing don't have MSS names
|  | SSPP | 23 | 3366 | 3360 | 3.16
|  | SUN_SAT | 23 | 3666 | 3437 | 0.24
|  | TEMP | 7 | 3666 | 3464 | 0.43
|  | VOLTAGE | 7 | 3666 | 3318 | 0.43
| L2 | SCANS_PARAM | 30 | 3666 | 3359 | 0.6 | 3359 | 0.6 | 30 | 3666 | 1806 | 0.27 |  |  | 9355 | 1.72
|  | SCANS_MID | 30 | 3666 | 3359 | 0.45 | 3359 | 0.45 |  |  | 3357 | 0.39
|  | SCANS_PROF | 30 | 3666 | 3369 | 1.23 | 3369 | 1.23 |  |  | 844 | 0.29
|  | SCANS_PROF_E | 35 | 818 | 530 | 0.17
PEM | PISW |  |  |  | 621 | 0.019097
| L0 |  | 4 | 3672 | 3662 | 119.2
| L1 | LOG | 4 | 3666 | 3474 | 0.25
| L2 | AAD | 4 | 3666 | 3475 | 16.83
|  | AAH | 4 | 3666 | 3475 | 0.24
|  | ABD | 4 | 3666 | 3475 | 16.4
|  | ABH | 4 | 3666 | 3475 | 0.24
|  | ACD | 4 | 3666 | 3475 | 5.98
|  | ACH | 4 | 3666 | 3475 | 0.24
|  | AE | 4 | 3666 | 3475 | 2.55
|  | HAD | 4 | 3666 | 3475 | 4.05
|  | HAH | 4 | 3666 | 3475 | 0.24
|  | HBD | 4 | 3666 | 3475 | 10.43
|  | HBH | 4 | 3666 | 3475 | 0.24
|  | HE | 4 | 3666 | 3475 | 3.21
|  | MAD | 4 | 3666 | 3475 | 27.71
|  | MAH | 4 | 3666 | 3475 | 0.24
|  | MBD | 4 | 3666 | 3475 | 15.55
|  | MBH | 4 | 3666 | 3475 | 0.24
|  | ME | 4 | 3666 | 3475 | 8.73
|  | OA | 4 | 3666 | 3641 | 40.78
|  | VAD | 4 | 3666 | 3475 | 0.45
|  | VAH | 4 | 3666 | 3475 | 0.24
|  | VMD | 4 | 3666 | 3475 | 60.96
|  | VMH | 4 | 3666 | 3475 | 0.24
ACRIM | L0 |  | 6 | 3672 | 3661 | 17.33
[5 empty] | 402557 | 1855.806 | 132567 | 1330.52 | [6 empty] | 167381 | 1353.2672
Legend:
|  |  |  | archive in progress or not started | [7 empty] | complete
verification in progress
not needed
Note on M160: Altan Gabbay: get remaining days from PC2 HD
Note on G26: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G27: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G28: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G29: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G33: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G35: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G36: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D26: Altan Gabbay: Days 35,36 & 37 not found in MSS
Note on D27: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D28: Altan Gabbay: Days 35,36 & 37 not found in MSS
Note on D29: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D33: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D35: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D36: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D37: Altan Gabbay: Not on MSS
Note on D38: Altan Gabbay: Not on MSS
Note on G37: Altan Gabbay: Not on MSS
Note on G38: Altan Gabbay: Not on MSS
Note on D40: Altan Gabbay: Not on MSS
Note on D39: Altan Gabbay: Not on MSS
Note on G39: Altan Gabbay: Not on MSS
Note on G40: Altan Gabbay: Not on MSS
Note on G41: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D41: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D42: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on G42: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D43: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on D44: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on D46: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on G43: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G44: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G46: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D47: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on G47: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D49: Altan Gabbay: Days 33 &34 not found in MSS
Note on D50: Altan Gabbay: Days 35, 36 & 37 not found in MSS
Note on G50: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D51: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G51: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D54: Altan Gabbay: Not on MSS
Note on G54: Altan Gabbay: Not on MSS
Note on D55: Altan Gabbay: Not on MSS
Note on G55: Altan Gabbay: Not on MSS
Note on D57: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G57: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D56: Altan Gabbay: Not on MSS
Note on G56: Altan Gabbay: Not on MSS
Note on D58: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on D59: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G58: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G59: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D65: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G65: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D74: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G74: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D75: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G75: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D76: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G76: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D77: Altan Gabbay: Days 33, 35 & 36 not on MSS
Note on G77: Altan Gabbay: Note 1 : Days 33,35,36&37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D78: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G78: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D80: Altan Gabbay: Day 33 not in MSS
Note on G80: Altan Gabbay: Day33 not found in MSS (UARSDB & SM/1 pointing to old 2GB platter)
Note on D81: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G81: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D82: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G82: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D83: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G83: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D84: Altan Gabbay: Days 35, 36 & 37 not on MSS
Note on G84: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on D10: Altan Gabbay: ORBIT_DEFINITIVE
Note on D11: Altan Gabbay: ORBIT_PREDICTIVEx
Note on D12: Altan Gabbay: Sub-Type: ATTITUDE_SSPPGIMBALS Days 2,522 and 3,668 to 3,672 did not return MSS names from UARSDB query
Note on Q157: Altan Gabbay: L2_SOLAR files need to be deleted
Note on D13: Altan Gabbay: ATTITUDE_EXTRSC
Note on Q129: Altan Gabbay: Day 681 not on MSS (points to old 2GB OCB platter). Days 2021 to 2064 need to be moved from /u4/mcb
Note on I26: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I27: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I28: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I29: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I33: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I35: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I36: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G24: Altan Gabbay: Days 5 to 14 and 35 to 46 are not on MSS (they point to old 2GB OBC platters)
Note on D24: Altan Gabbay: Days 5 to 14 and 35 to 46 are not on MSS (they point to old 2GB OBC platters)
Note on D130: Altan Gabbay: Day 513 not in MSS (points to old 2GB OCB platter)
Note on Q12: Altan Gabbay: Days 2,522 and 3,668 to 3,672 did not return MSS names from UARSDB query
Note on Q13: Altan Gabbay: Days 2,522 and 3,668 to 3,672 did not return MSS names from UARSDB query
Note on G49: Altan Gabbay: Days 33 & 34 not found on MSS. UARSDB points to old 2GB (OCB) platters
Note on I41: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I42: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I43: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I44: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I46: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I47: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I49: Altan Gabbay: Days 33 & 34 not found on MSS. UARSDB points to old 2GB (OCB) platters
Note on I50: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I51: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I57: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I58: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I59: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I65: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I74: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I75: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I76: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I77: Altan Gabbay: Note 1 : Days 33,35 & 36 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I78: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I80: Altan Gabbay: Day33 not found in MSS (UARSDB & SM/1 pointing to old 2GB platter)
Note on I81: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I82: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I83: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on I84: Altan Gabbay: Note 1 : Days 35,36 & 37 not on MSS (UARSDB & SM/1 point to the old 2GB OCB platters)
Note on G93: Altan Gabbay: Days 5, 6 & 277 not on MSS (UARSDB & SM/1 point to old OCB 2GB platter)
Note on G117: Altan Gabbay: Day 3,666 not found on MSS (UARSDB & SM/1 point to old OCB 2GB platter)
Note on G129: Altan Gabbay: Day 681 not on MSS (UARSDB & SM/1 point to old 2GB OCB platter).
Note on Q131: Altan Gabbay: Encountering MSS platter problems with OAD:376C558B:A
Note on Q18: Altan Gabbay: Days 603 to 629 are not needed and can be deleted from DIRAC (they are not shown here)
Note on M12: Altan Gabbay: Days 2,522 and 3,668 to 3,672 did not return MSS names from UARSDB query
Note on M13: Altan Gabbay: Days 2,522 and 3,668 to 3,672 did not return MSS names from UARSDB query
Note on Q87: Altan Gabbay: L0 days with no corresponding L1 file not copied!
Note on M87: Altan Gabbay: L0 days with no corresponding L1 file not copied!
Note on Q86: Altan Gabbay: Two files on problem platter OAD31751117 could not be read CAL_SMLS_L2_D0001.XL2PC01FA_010_V0001_C01_PROD CAL_SMLS_L2_D0001.XL2PC01FN_010_V0001_C01_PROD
Note on M86: Altan Gabbay: Two files on problem platter OAD31751117 could not be read CAL_SMLS_L2_D0001.XL2PC01FA_010_V0001_C01_PROD CAL_SMLS_L2_D0001.XL2PC01FN_010_V0001_C01_PROD
Note on G147: Altan Gabbay: 29 files XSOL_CRH_PREV & XSOL_CRH_NEW not found on MSS (They point to old 2GB "OCB" platters)
Note on D119: Altan Gabbay: Encountering many files on problem platters: namely OAD"31751117" will need to go back to problem platters after other transfers are completed.
Note on M16: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q16: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M21: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q21: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M85: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q85: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M95: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q95: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M118: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q118: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M132: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q132: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M146: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q146: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M158: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q158: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on M194: Altan Gabbay: VMS Backup Save Set stored on CDHFB (mini-CDHF)
Note on Q194: Altan Gabbay: TAR file and VMS Backup Save Set stored on DIRAC
Note on Q190: Altan Gabbay: Need to sort by sub-types to complete verification
Note on M195: Altan Gabbay: (99% Done except for bad platters FTH)
Note on Q195: Altan Gabbay: (99% Done except for bad platters FTH)
Note on M219: Altan Gabbay: (99% Done except for bad platters FTH)
Note on Q219: Altan Gabbay: (99% Done except for bad platters FTH)